## Ark1
1.iterasjon |  |  |  | Sannsynlighet
|  | Risiko | Veldig lav | Lav | Middels | Høy | Veldig høy
Veldig lav
|  | Lav |  | R7 | R6
| Alvorlighet | Middels
|  | Høy |  | R5 | R3
|  | Veldig høy | R2 | R1, R4
2.iterasjon |  |  |  | Sannsynlighet
|  | Risiko | Veldig lav | Lav | Middels | Høy | Veldig høy
Veldig lav
Lav
| Alvorlighet | Middels
Høy
Veldig høy
3.iterasjon
Degree of Consequence
|  | Risk | Insignificant | Minor | Significant | Major | Critical
|  | Almost certain | 5 | 10 | 15 | 20 | 25 | Risk criteria
|  | Likely | 4 | 8 | 12 | 16 | 20 | Level | Measure
Degree of Probability |  | Possible | 3 | 6 | 9 | 12 | 15 | High Risk | Unacceptable, and action must be taken immediately.
|  | Unlikely | 2 | 4 | 6 | 8 | 10 | Medium Risk | Need to implement measures to reduce risk.
|  | Rare | 1 | 2 | 3 | 4 | 5 | Low Risk | Acceptable, but measures should be taken where feasible
Risk = Probability x Consequence
4.iterasjon
Degree of Consequence
|  | Risk | Insignificant | Minor | Significant | Major | Critical
|  | Almost certain | 4 | 8 | 12 | 16 | 20 | Risk criteria
|  | Likely | 3 | 6 | 9 | 12 | 15 | Level | Measure
Degree of Probability |  | Possible | 2 | 4 | 6 | 8 | 10 | High Risk | Unacceptable, and action must be taken immediately.
|  | Unlikely | 1 | 2 | 3 | 4 | 5 | Medium Risk | Need to implement measures to reduce risk.
[8 empty] | Low Risk | Acceptable, but measures should be taken where feasible
|  | Definition of probability for the project | [5 empty] | Definition of consequence for the project
|  | Level | Degree of probability |  | Frequency |  |  | Level | Degree of consequence | Outcome
|  | 1 | Unlikely |  | Happens very rarely |  |  | 1 | Insignificant | Project continues as normal.
|  | 2 | Possible |  | Happens rarely |  |  | 2 | Minor | Project becomes delayed slightly, but minimal effects on the end results.
|  | 3 | Likely |  | Happens sometimes |  |  | 3 | Significant | Project stagnates, measures required.
|  | 4 | Almost certain |  | Happens often |  |  | 4 | Major | Project stops, critical measures required.
[8 empty] | 5 | Critical | Project falls apart. All measures must be put in place to continue.